## DNREC
Biannual Program Snapshot
Program Administrator: |  | DNREC
Report Date: |  | 2024-09-10
Calendar Year: |  | 2024
Report Period: |  | Q1-Q2
Snapshot Populated By (Point of Contact): |  | Gretchen Calcagni
Program | Sector (Residential, Low Income, C&I, Non-profit) | Gross Annual Electric Savings (kWh) - No Fuel Switching |  | Gross Peak Demand Reduction (kW) |  | Gross Annual Gas Savings (MMBtu) |  | Gross Annual Oil/Propane Savings (MMBtu) |  | Gross Annual All Fuel Energy Savings (MMBtu) |  | # of Projects Completed through Efficiency Programs (Examples include # of homes, businesseses, customers, buildings, sites, units etc.) |  | Program Budget (Measures, Labor, and Admin)
|  | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2)
WAP | Low Income | 444170 | 199710 | 78 | 30.66 | 806 | 525 | 2856 | 886.7 | 5177.508 | 2093.1105 | 400 | 160 | 4153356 | 2505356.6
EEIF | C&I | 24913440 | 3121241.74 | 2450 | 551.59 | 31920 | 8240.83 | 0 | 0 | 116924.6573 | 18632.6768 | 120 | 62 | 5000000 | 1087014.96
Total Portfolio - All Programs |  | 25357610 | 3320951.74 | 2528 | 582.25 | 32726 | 8765.83 | 2856 | 886.7 | 122102.1653 | 20725.7873 | 520 | 222 | 9153356 | 3592371.56
kWh to MMBtu Conversion Factor | 0.003412
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These columns should include all electric, gas, and delivered fuel energy impacts including any increased usage from fuel switching.

## DPL
Biannual Program Snapshot
Program Administrator: |  | DPL
Report Date: |  | 2024-10-07
Calendar Year: |  | 2024
Report Period: |  | Q1-Q2
Snapshot Populated By (Point of Contact): |  | Joe Cohen
Program | Sector (Residential, Low Income, C&I, Non-profit) | Gross Annual Electric Savings (kWh) - No Fuel Switching |  | Gross Peak Demand Reduction (kW) |  | Gross Annual Gas Savings (MMBtu) |  | Gross Annual Oil/Propane Savings (MMBtu) |  | Gross Annual All Fuel Energy Savings (MMBtu) |  | # of Projects Completed through Efficiency Programs (Examples include # of homes, businesseses, customers, buildings, sites, units etc.) |  | Program Budget (Measures, Labor, and Admin)
|  | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2)
Behavioral | Residential | 18923119.8809 | 9204206.9993 | 4368.3918 | 8365.7948 |  |  |  |  | 64565.685 | 31404.7543 | 185000 | 181030 | 999000 | 411069
Energy Star for New Homes | Residential | 646872.6731 | 0 | 213.3185 | 0 |  |  |  |  | 2207.1296 | 0 | 26 | 0 | 788400 | 101873
QHEC | Residential | 1408227.8481 | 78183.172 | 83.4725 | 4257.0952 |  |  |  |  | 4804.8734 | 266.761 | 225 | 120 | 709341 | 11750
Total Portfolio - All Programs |  | 20978220.4021 | 9282390.1713 | 4665.1827 | 12622.89 | 0 | 0 | 0 | 0 | 71577.688 | 31671.5153 | 185251 | 181150 | 2496741 | 524692
kWh to MMBtu Conversion Factor | 0.003412
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These columns should include all electric, gas, and delivered fuel energy impacts including any increased usage from fuel switching.

## DEMEC
Biannual Program Snapshot
Program Administrator: |  | DEMEC
Report Date: |  | 2024-10-08
Calendar Year: |  | 2024
Report Period: |  | Q1-Q2
Snapshot Populated By (Point of Contact): |  | Maya Krasker
Program | Sector (Residential, Low Income, C&I, Non-profit) | Gross Annual Electric Savings (kWh) - No Fuel Switching |  | Gross Peak Demand Reduction (kW) |  | Gross Annual Gas Savings (MMBtu) |  | Gross Annual Oil/Propane Savings (MMBtu) |  | Gross Annual All Fuel Energy Savings (MMBtu) |  | # of Projects Completed through Efficiency Programs (Examples include # of homes, businesseses, customers, buildings, sites, units etc.) |  | Program Budget (Measures, Labor, and Admin)
|  | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2)
Home Energy Rebates | Residential | n/a | 42494 | n/a | 7 | n/a | n/a | n/a | n/a | n/a | 144.9895 | n/a | 47
Online Savings Store | Residential | n/a | 1208 | n/a | 1 | n/a | n/a | n/a | n/a | n/a | 4.1217 | n/a | 6
Local Retail Savings | Residential | n/a | 0 | n/a | 0 | n/a | n/a | n/a | n/a | n/a | 0 | n/a | 0
Appliance Recycling Rewards | Residential | n/a | 0 | n/a | 0 | n/a | n/a | n/a | n/a | n/a | 0 | n/a | 0
Large Business Solutions | C&I | n/a | 755463 | n/a | 129 | n/a | n/a | n/a | n/a | n/a | 2577.6398 | n/a | 21
Small Business Solutions | C&I | n/a | 55782 | n/a | 18 | n/a | n/a | n/a | n/a | n/a | 190.3282 | n/a | 6
Total Portfolio - All Programs |  | 0 | 854947 | 0 | 155 | 0 | 0 | 0 | 0 | 0 | 2917.0792 | 0 | 80 | 1313868 | 656934
kWh to MMBtu Conversion Factor | 0.003412
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These columns should include all electric, gas, and delivered fuel energy impacts including any increased usage from fuel switching.

## DESEU
Biannual Program Snapshot
Program Administrator: |  | DESEU
Report Date: |  | 2024-10-14
Calendar Year: |  | 2024
Report Period: |  | Q1-Q2
Snapshot Populated By (Point of Contact): |  | Athena Bi
Program | Sector (Residential, Low Income, C&I, Non-profit) | Gross Annual Electric Savings (kWh) - No Fuel Switching |  | Gross Peak Demand Reduction (kW) |  | Gross Annual Gas Savings (MMBtu) |  | Gross Annual Oil/Propane Savings (MMBtu) |  | Gross Annual All Fuel Energy Savings (MMBtu) |  | # of Projects Completed through Efficiency Programs (Examples include # of homes, businesseses, customers, buildings, sites, units etc.) |  | Program Budget (Measures, Labor, and Admin)
|  | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2)
Faith Efficiency1 |  | 83539 |  | 32 |  | 1766 |  |  |  | 2051.0351 | 0 | 7 |  | 41188 | 1923
Farm Program2 |  | 215722 |  | 1337 |  | 3225 |  |  |  | 3961.0435 | 2437 | 33 | 3 |  | 134867
Home Performance Program3 |  | 3800022 | 705558 | 937 | 250 | 8407 | 23231 |  | 18753 | 21372.6751 | 44391.3639 | 4147 | 3892 | 5902690 | 4349420
Energy Assessment for Non-profit |  | 1591163 | 257627 | 586 |  | 4466 | 724 |  |  | 9895.0482 | 1603.0233 | 23 | 6 | 93917 | 75000
Pathway to Green Ribbon Schools4 |  | 237534 |  | 92 |  | 49 |  |  |  | 859.466 | 0 | 8 |  | 96479 | 112362
Performance Contracting5 |  | 17116226 |  | 15904 |  | 151142 |  |  |  | 209542.5631 | 0 | 5 |  | 8000000
Revolving Loan Fund |  | 2325719 | 2169239 | 983 |  | 13388 | 2957 |  |  | 21323.3532 | 10358.4435 | 22 | 6 | 6000000 | 3647277
Home Energy Checkup & Counseling |  | 218451 | 20268 | 23 | 402 | 15294 | 92 |  | 4.3 | 16039.3548 | 165.4544 | 315 | 200 | 577697 | 230480
Affordable Multifamily Housing6 |  | 816397 | 122099 |  |  | 10248 |  |  |  | 13033.5466 | 416.6018 | 41 | 3 | 798539.81 | 835998.5
Online Marketplace |  | 394947 | 173696 | 8 | 1.18 | 1100 | 560.8 |  |  | 2447.5592 | 560 | 2604 | 204 | 173867 | 205130
PACE6 |  | 1655877.2 |  | 55.2 |  | 763244.4 |  |  |  | 768894.253 | 0 | 6 | 1 | 8000000 | 45933.67
Non-Profit EEIF | [9 empty] | 0 | 0 |  | 2 |  | 134867
Pre-Weatherization | [9 empty] | 0 | 0 |  |  |  | 1032513
Challenge ESPC | [14 empty] | 1600000
Small Business Performance Program | [14 empty] | 12339
Energize Delaware Climate Smart Home | [9 empty] | 0 | 0 |  |  |  | 21420
Total Portfolio - All Programs |  | 28455597.2 | 3448487 | 19957.2 | 653.18 | 972329.4 | 27564.8 | 0 | 18757.3 | 1069419.8976 | 59931.8869 | 7211 | 4317 | 29684377.81 | 12439530.17
kWh to MMBtu Conversion Factor | 0.003412 | 0.003412
Note
1. Faith Efficiency is now an energy ambassador for the faith community. The assessment were conducted through Energy Asssment for Non-profit. If funded, the funding will be provided through Revolving Loan Fund .
2. Farm program is under revamp and managed in house. We are actively looking for program partner but the performance will not be as high as projected, since it considered the program implimentor impact on the program.
3. The projects in Q1-Q2 has a lower than projected kWh saving, but much higher MMBtu savings from Gas, Oil and Propane.
4. Pathway to Green Ribbon School have Assessment done in Q1-Q2, but there is no followup survey responses to report for this time.
5. We will report on the Performance Contracting Program at the end of the year.
6. The Afforadable Multifamily Housing will only reported on the measures which's all incentives were awarded. There is a delay in the reporting due to this. We expect to see the number increase faster in the later half of the year.
6. There is one PACE project closed late August, which will be reported in Q3-Q4.
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These columns should include all electric, gas, and delivered fuel energy impacts including any increased usage from fuel switching.
Note on N12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No. Households
Note on M18: Athena Bi: We used to plan by number of units.
Note on N18: Athena Bi: Number of Buildings

## DEC
Biannual Program Snapshot
Program Administrator: |  | DEC
Report Date: |  | 2024-10-14
Calendar Year: |  | 2024
Report Period: |  | Q1-Q2
Snapshot Populated By (Point of Contact): |  | JD
Program | Sector (Residential, Low Income, C&I, Non-profit) | Gross Annual Electric Savings (kWh) - No Fuel Switching |  | Gross Peak Demand Reduction (kW) |  | Gross Annual Gas Savings (MMBtu) |  | Gross Annual Oil/Propane Savings (MMBtu) |  | Gross Annual All Fuel Energy Savings (MMBtu) |  | # of Projects Completed through Efficiency Programs (Examples include # of homes, businesseses, customers, buildings, sites, units etc.) |  | Program Budget (Measures, Labor, and Admin)
|  | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2) | Planned (Annual) | Actual (As of end of Q2)
EV Charging DR Program | Residential | 0 | 0 | 3000 | 1453 |  |  |  |  | 0 | 0 | 400 | 337 | 40000 | 15000
Roadway Area Lighting | C&I | 190000 | 184416 |  | 0 |  |  |  |  | 648.28 | 629.2274 | 1000 | 583 | 1000000 | 535504
Heat Pump Water Heater | Residential | 3000 | 2724 |  | 0 |  |  |  |  | 10.236 | 9.2943 | 3 | 2 | 8000 | 5525
Thermostat Program | Residential | 100000 | 23636 |  | 3530 |  |  |  |  | 341.2 | 80.646 | 4000 | 2402 | 150000 | 51125
Low Income | Residential | 3000 | 0 | [6 empty] | 10.236 | 0 | 0 | 0 | 0 | 0
HPwES | Residential | 100000 | 145037 |  | 20 |  | 20 |  |  | 341.2 | 514.8662 | 600 | 327 | 250000 | 29075
Total Portfolio - All Programs |  | 396000 | 355813 | 3000 | 5003 | 0 | 20 | 0 | 0 | 1351.152 | 1234.034 | 6003 | 3651 | 1448000 | 636229
kWh to MMBtu Conversion Factor | 0.003412
Note on K8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: These columns should include all electric, gas, and delivered fuel energy impacts including any increased usage from fuel switching.

## Statewide
Planned Data based on Three Year Program Plans; Actual Data based on Data reported in Biannual Snapshot
PA | Gross Annual Electric Savings (kWh) |  | Peak Demand Reduction (kW) |  | Gross Annual Gas Savings (MMBtu) |  | Gross Annual Oil/Propane Savings (MMBtu) |  | # of Projects Completed through Efficiency Programs (Examples include # of homes, businesseses, customers, buildings, sites, units etc.) |  | Program Budget (Measures, Labor, and Admin)
| Planned (Annual) | Actual (Q1-Q2) | Planned (Annual) | Actual (Q1-Q2) | Planned (Annual) | Actual (Q1-Q2) | Planned (Annual) | Actual (Q1-Q2) | Planned (Annual) | Actual (Q1-Q2) | Planned (Annual) | Actual (Q1-Q2)
DEMEC | 2477800 | 854947 | 329 | 155 | n/a | n/a | n/a | n/a | n/a | 80 | 886581 | 656934
DESEU | 52164496 | 3448487 | 20747 | 653.18 | 1356574 | 27564.8 | n/a | 18757.3 | 14539 | 4317 | 31568049.81 | 12439530.17
DPL | 0
DNREC | 25357610 | 3320951.74 | 2528 | 582.25 | 32726 | 8765.83 | 2856 | 886.7 | 520 | 222 | 9153356 | 3592371.56
DEC | 1400000 | 355813 | 21050 | 5003 | 650 | 20 | n/a | n/a | 2851 | 3651 | 1911000 | 636229
DPL | 20978220.4021 | 9282390.1713 | 4665.1827 | 12622.89 | n/a | n/a | n/a | n/a | 185251 | 181150 | 2496741 | 524692
Total | 75588109 | 7980198.74 | 42519 | 6393.43 | 1211824 | 36350.63 | 2856 | 19644 | 15923 | 8270 | 41914656 | 17325064.73
$/kwh
DEMEC | #REF! | #REF!
DESEU | 0.60516 | 3.6072
DPL | #DIV/0! | #DIV/0!
DNREC | 0.35781 | 4.2019
Total | 0.55451 | 2.171