## Master
Delaware
Energy Efficiency Advisory Council
Planning Calendar | 2018 |  |  |  | 2019 | [11 empty] | 2020
Tasks |  | Quarter 4 |  |  | Quarter 1 |  |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4 |  |  | Quarter 1 |  |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4
| Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
General Council
PA Program updates | bar: Quarter 1 Mar
PA Data Migration | bar: Quarter 1 Mar; Quarter 2 Jun; Quarter 3 Sep; Quarter 4 Dec
Biannual Program Snapshot Presentations | bar: Quarter 1 Mar; Quarter 3 Sep
EEAC Consultant Annual Cost-Effectiveness Memo and Presentation | bar: Quarter 1 Mar
Low-Income Committee Annual Report | bar: Quarter 2 Apr
EEAC Annual Report | bar: Quarter 1 Mar; Quarter 4 Dec
Annual Reconciliation Reports | bar: Quarter 1 Jan
Three-Year Target Planning
EEAC Discussions on EE MarketProgram Trends
Update Potential Study | bar: Quarter 1 Jan
EEAC Discussion re: savings targets (Electric) | bar: Quarter 1 Jan; Quarter 1 Mar
EEAC sets recommended portfolio and savings targets (Electric) | bar: Quarter 2 May
Potential Evaluation/Analysis of Gas Programs | bar: Quarter 1 Jan
PAs submit three-year plans to the EEAC (Electric Only) | bar: Quarter 3 Jul
PAs submit three-year plans to the PSC | bar: Quarter 3 Jul
PSC votes on three-year plans | bar: Quarter 4 Dec
Delmarva
PA Program updates
Data Migration | bar: Quarter 3 Sep; Quarter 4 Dec
Assess Potential for gas program(s) | bar: Quarter 1 Jan to Quarter 1 Mar
Electric Program Approved by PSC
Electric Program EM&V Plan approved | bar: Quarter 2 Apr
Electric Program Starts and runs | bar: Quarter 3 Jul to Quarter 4 Dec
Chesapeake
PA Program updates | bar: Quarter 1 Mar
Assess potential for gas program(s) | bar: Quarter 1 Jan to Quarter 1 Mar
COOP (PENDING)
PA Program updates | bar: Quarter 1 Mar
Data Migration | bar: Quarter 1 Mar; Quarter 2 Jun; Quarter 3 Sep; Quarter 4 Dec
Electric Program Running
DEMEC (PENDING
PA Program updates | bar: Quarter 1 Mar
PA Data Migration | bar: Quarter 1 Mar; Quarter 2 Jun; Quarter 3 Sep; Quarter 4 Dec
Electric Program Running
SEU
PA Program updates
PA Data Migration
Electric Program
Gas Programs
DNREC
PA Program updates | bar: Quarter 1 Mar
PA Data Migration | bar: Quarter 1 Mar; Quarter 2 Jun; Quarter 3 Sep; Quarter 4 Dec
Electric Program Running
Gas program starts and runs